## Sheet1
TASK | START DATE | DURATION
Look at requirements/Brainstorm | 2018-03-14 | 1
Begin to design project | 2018-03-15 | 2
Laying out schematics of project | 2018-03-17 | 3
Coding and implementing design | 2018-03-15 | 14
Adding features | 2018-03-28 | 4
Testing | 2018-04-01 | 2
Improving design | 2018-04-01 | 5
Creating any add-ons | 2018-04-06 | 1
Project 3 Documentation | 2018-04-03 | 5
Final testing/bugs | 2018-04-08 | 1
Prepare for presentation | 2018-04-08 | 2
Requirements for project 4/Brainstorming | 2018-04-06 | 10
Design of added features | 2018-04-16 | 5
Coding/implementing design | 2018-04-12 | 17
Testing for project 4 | 2018-04-29 | 4
Changing code after testing | 2018-04-30 | 3
Updating Documentation | 2018-05-01 | 3
Prepare for presentation | 2018-05-06 | 7