## Sheet1
Task | Start Date | Duration
Look at requirements/Brainstorm | 2018-03-14 | 1
Begin to design project | 2018-03-15 | 2
Laying out schematics of project | 2018-03-17 | 3
Coding and implementing design | 2018-03-20 | 7
Adding features | 2018-03-28 | 4
Testing | 2018-04-01 | 2
Improving design | 2018-04-03 | 3
Creating any add-ons | 2018-04-06 | 1
Final testing/bugs | 2018-04-07 | 1
Prepare for presentation | 2018-04-08 | 2
Requirements for project 4 | 2018-04-11 | 2
Design of added features | 2018-04-13 | 4
Coding/implementing design | 2018-04-17 | 7
Testing for project 4 | 2018-04-23 | 3
Finalize code for added features/documentation | 2018-04-27 | 7
Prepare for presentation | 2018-05-04 | 2